## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Cyber Risk Platform | MUST HAVE | No Dependency | Nikhitha Mondeddu | 3-Completed
S1 | S1 | US-001 | Setup Nmap scanning module | MUST HAVE | Nmap | Nikhitha Mondeddu | 3-Completed
S2 | S2 | US-001 | Integrate VirusTotal API | MUST HAVE | VT API | Nikhitha Mondeddu | 3-Completed
S2 | S2 | US-001 | Develop Risk Scoring Engine | MUST HAVE | Python | Nikhitha Mondeddu | 3-Completed
S3 | S3 | US-001 | Build Dashboard UI (Streamlit) | MUST HAVE | Streamlit | Nikhitha Mondeddu | 3-Completed
S3 | S3 | US-001 | Implement Charts (Pie, Bar, Scatter) | SHOULD HAVE | Plotly | Nikhitha Mondeddu | 3-Completed
S4 | S4 | US-001 | Add Heatmap Visualization | SHOULD HAVE | Plotly | Nikhitha Mondeddu | 3-Completed
S4 | S4 | US-001 | Threat Intelligence Integration | MUST HAVE | VirusTotal | Nikhitha Mondeddu | 3-Completed
S5 | S5 | US-001 | Email Alert System (SMTP) | MUST HAVE | Gmail API | Nikhitha Mondeddu | 3-Completed
S6 | S6 | US-001 | PDF Report Generation | MUST HAVE | FPDF | Nikhitha Mondeddu | 3-Completed
S7 | S7 | US-001 | Database Integration (SQLite) | SHOULD HAVE | SQLite | Nikhitha Mondeddu | 2-In Progress
S7 | S7 | US-001 | Scan History Page | SHOULD HAVE | Database | Nikhitha Mondeddu | 2-In Progress
S8 | S8 | US-001 | Auto Alert on Critical Risk | MUST HAVE | Email Module | Nikhitha Mondeddu | 2-In Progress
S8 | S8 | US-001 | Risk Meter (Gauge Chart) | SHOULD HAVE | Plotly | Nikhitha Mondeddu | 2-In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Setup project and environment | 2026-02-06 | 2026-02-06 | Nikhitha Mondeddu | Setup | 3-Completed | 4
US-001 | 2 | Implement Nmap scan | 2026-02-08 | 2026-02-09 | Nikhitha Mondeddu | Coding | 3-Completed | 6
US-001 | 3 | Integrate VirusTotal API | 2026-02-10 | 2026-02-13 | Nikhitha Mondeddu | Coding | 3-Completed | 8
US-001 | 4 | ¦ Build risk scoring logic | 2026-02-15 | 2026-02-20 | Nikhitha Mondeddu | Coding | 3-Completed | 5
US-001 | 5 | Create Streamlit dashboard | 2026-02-22 | 2026-02-24 | Nikhitha Mondeddu | Build | 3-Completed | 10
US-001 | 6 | Add charts and graphs | 2026-02-26 | 2026-02-28 | Nikhitha Mondeddu | Build | 3-Completed | 8
US-001 | 7 | Heatmap implementation | 2026-03-02 | 2026-03-06 | Nikhitha Mondeddu | Build | 3-Completed | 6
US-001 | 8 | Threat intelligence panel | 2026-03-06 | 2026-03-10 | Nikhitha Mondeddu | Coding | 3-Completed | 6
US-001 | 9 | Email alert system | 2026-03-10 | 2026-03-15 | Nikhitha Mondeddu | Integration | 3-Completed | 7
US-001 | 10 | PDF report generation | 2026-03-15 | 2026-03-19 | Nikhitha Mondeddu | Build | 3-Completed | 6
US-001 | 11 | Database storage | 2026-03-19 | 2026-03-22 | Nikhitha Mondeddu | Integration | 2-In Progress | 7
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint 2 | Day 6 | API integration delay | Reviewed documentation and fixed API calls
sprint 2 | Day 7 | Risk logic confusion | finalized scoring
sprint 3 | Day 9 | UI alignment issues | Redesigned layout using Streamlit columns
sprint 3 | Day 12 | Chart visualization errors | Fixed plotting logic
sprint 4 | Day 16 | Email sending failure | Configured SMTP and app password
sprint 5 | Day 23 | PDF formatting issue | Improved layout and fixed encoding
sprint 6 | Day 25 | Database errors | Debugged SQLite queries
sprint 7 | Day 28 | Performance delay | Optimized scan execution

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-02-04 | 2026-02-13 | Nikhitha Mondeddu | Planning tasks clearly | Skipping documentation | Team collaboration | Created clear backlog
2 | sprint 2 | 2026-02-15 | 2026-02-24 | Nikhitha Mondeddu | API testing regularly | Ignoring edge cases | Debugging actively | Improved API handling
3 | sprint 3 | 2026-02-25 | 2026-03-01 | Nikhitha Mondeddu | Designing UI early | Last-minute UI fixes | Iterative improvements | Refined dashboard
4 | sprint 4 | 2026-03-02 | 2026-03-07 | Nikhitha Mondeddu | Testing features | Rushing integrations | Code reviews | Stabilized system
5 | sprint 5 | 2026-03-08 | 2026-03-13 | Nikhitha Mondeddu | Improving reports | Ignoring formatting | Documentation | Enhanced Pdf
6 | sprint 6 | 2026-03-13 | 2026-03-22 | Nikhitha Mondeddu | Performance tuning | Inefficient loops | Optimization | Improved Speed